## Template
SSLM · Simple Solution, Low Maintenance | [5 empty] | Project Plan · Template
Project Plan
The spine of the framework — the milestones everything else rolls up to.
How to use — one row per milestone. Give each an ID (M1, M2…) the RAID log and weekly report link to. Set Level 1–5 — Level 1 is the strategic milestone tied to an organisational objective, Level 5 the lowest project detail; levels drive the roll-up and set reporting altitude. Note any RAID item this milestone depends on (e.g. D001). Status colours automatically. Reference must match the number assigned on the PTIP — format YYYY-NNN, e.g. 2026-001.
Project |  |  |  | Project manager |  |  |  | Project Sponsor
|  |  |  | Strategic objective |  |  |  | Reporting date
Reference
ID | Level | Phase | Milestone / deliverable | Owner | Start | Due | Status | Progress | Critical path? | Dependency (RAID) | Notes

## Example
SSLM · Simple Solution, Low Maintenance | [5 empty] | Project Plan · Worked example
Project Plan
The spine of the framework — the milestones everything else rolls up to.
How to use — one row per milestone. Give each an ID (M1, M2…) the RAID log and weekly report link to. Set Level 1–5 — Level 1 is the strategic milestone tied to an organisational objective, Level 5 the lowest project detail; levels drive the roll-up and set reporting altitude. Note any RAID item this milestone depends on (e.g. D001). Status colours automatically. Reference must match the number assigned on the PTIP — format YYYY-NNN, e.g. 2026-001.
Project | Customer Portal Launch |  |  | Project manager | A. Chen |  |  | Project Sponsor | M. Rivera
|  |  |  | Strategic objective | Improve customer self-service; reduce inbound call volume |  |  | Reporting date | 30 Jun 2026
Reference | 2026-001
ID | Level | Phase | Milestone / deliverable | Owner | Start | Due | Status | Progress | Critical path? | Dependency (RAID) | Notes
M1 | 2 | Scoping | Requirements confirmed & signed off | A. Chen | 05 May 2026 | 16 May 2026 | Green | 100% | Yes |  | Baseline scope agreed with sponsor
M2 | 3 | Design | UX & solution design signed off | R. Okafor | 19 May 2026 | 30 May 2026 | Green | 100% | Yes |  | Configure over customise; one platform
M3 | 3 | Build | Portal build complete | R. Okafor | 02 Jun 2026 | 27 Jun 2026 | Amber | 60% | Yes | AS001 | Slightly behind on content load
M4 | 4 | Build | Identity / SSO integration | Vendor + IT | 09 Jun 2026 | 27 Jun 2026 | Red | 30% | Yes | D001, I001, R001 | Blocked — vendor slippage
M8 | 5 | Build | SSO test environment configured | Vendor + IT | 09 Jun 2026 | 13 Jun 2026 | Green | 100% | No |  | Confirms SSO config ahead of full integration testing under M4
M5 | 3 | Test | UAT complete | Business testers | 30 Jun 2026 | 11 Jul 2026 | Green | 0% | Yes | R002 | At risk if SSO not cleared
M6 | 1 | Go-Live | Go-live | A. Chen | 14 Jul 2026 | 18 Jul 2026 | Green | 0% | Yes |  | Fallback auth kept as roll-back
M7 | 2 | Post Go-Live | Handover & benefit baseline | A. Chen | 21 Jul 2026 | 25 Jul 2026 | Green | 0% | No |  | Capture baseline call volume before go-live