## Template
SSLM · Simple Solution, Low Maintenance | Executive Stream One-Pager · Template
Executive Stream One-Pager
One page per value stream — the five elements a board decides on, with agile telemetry left below the line.
How to use — derive this from the weekly flow once per governance cycle; never re-author. See the Flow-to-Executive Translation Guide for the mapping and the integrity check. Every status must trace to a real flow signal.
Value stream | Owner | Reporting date
Overall status
Element | Status | Summary & decision needed
Alignment
Confidence
Constraint
Value
Investment

## Example
SSLM · Simple Solution, Low Maintenance | Executive Stream One-Pager · Example
Executive Stream One-Pager
One page per value stream — the five elements a board decides on, with agile telemetry left below the line.
How to use — derive this from the weekly flow once per governance cycle; never re-author. See the Flow-to-Executive Translation Guide for the mapping and the integrity check. Every status must trace to a real flow signal.
Value stream | Owner | Reporting date
Payments Platform | D. Owner | 30 Jun 2026
Overall status | Amber
Element | Status | Summary & decision needed
Alignment | Green | Serves “grow transaction revenue”. On strategy.
Confidence | Amber | Committed launch end-Q3 at risk. Decision: clear the integration blocker or reset the date.
Constraint | Red | Third-party payment gateway integration is the bottleneck; two sprints of flow lost.
Value | Green | Released capability (card payments) is live and being used in production.
Investment | Amber | Spend is buying flow, but the constraint means recent spend hasn't converted to release. Hold, revisit next cycle.