## Template
| SSLM · Simple Solution, Low Maintenance |  | RACI · Template
RACI
Roles against plan activities — collaborate on the work, be clear on who answers for it.
How to use — one row per plan activity or deliverable. Exactly one Accountable per row — the single owner who answers for it. Responsible does the work; Consulted give input; Informed are kept in the loop.
| Project | Project manager | Reporting date
Reference
RACI ID | Activity / deliverable | R (Responsible) | A (Accountable) | C (Consulted) | I (Informed)

## Example
| SSLM · Simple Solution, Low Maintenance |  | RACI · Worked example
RACI
Roles against plan activities — collaborate on the work, be clear on who answers for it.
How to use — one row per plan activity or deliverable. Exactly one Accountable per row — the single owner who answers for it. Responsible does the work; Consulted give input; Informed are kept in the loop.
| Project | Project manager | Reporting date | 30 Jun 2026
| Reference | 2026-001
RACI ID | Activity / deliverable | R (Responsible) | A (Accountable) | C (Consulted) | I (Informed)
RACI001 | Requirements sign-off (M1) | PM | Business Owner | Business, IT | SteerCo
RACI002 | Solution design (M2) | Developer | PM | Sponsor, IT | Team
RACI003 | Portal build (M3) | Developer | PM | Content author | Sponsor
RACI004 | SSO integration (M4) | Vendor | PM | IT | SteerCo
RACI005 | UAT (M5) | Business testers | PM | Developer | Sponsor
RACI006 | Go-live cutover (M6) | PM | Business Owner | Vendor, Ops | SteerCo
RACI007 | Handover & benefit baseline (M7) | PM | Business Owner | Ops manager | SteerCo