## Template
SSLM · Simple Solution, Low Maintenance |  |  | Stakeholder & Communication Plan · Template
Stakeholder & Communication Plan
Part A maps who matters and how much. Part B turns that map, plus the RACI, into an actual schedule of communications.
How to use — revisit the stakeholder map at each stage gate. Build the communication plan from it: who needs what, how often, and in what format.
Project |  | Reference |  | Review date
Part A — Stakeholder Map
Stakeholder / group | Role | Interest (L/M/H) | Influence (L/M/H) | Quadrant | Engagement approach
Project Sponsor
Business Owner
SteerCo members
Project team
Vendor(s)
BoM
End users
Part B — Communication Plan
Communication / meeting | Purpose | Audience | Frequency | Format / method | Owner
Kick-off meeting |  |  | Once, at project start | Meeting
Weekly Update |  |  | Weekly
Team meeting |  |  | Weekly | Meeting
SteerCo Pack & meeting |  |  | Each SteerCo cycle | Meeting + pack
Monthly Report to BoM |  |  | Monthly | Report
Sponsor / Business Owner briefing |  |  | As needed | Meeting
Closure & lessons learned review |  |  | At project closure | Meeting + report

## Example
SSLM · Simple Solution, Low Maintenance |  |  | Stakeholder & Communication Plan · Worked example
Stakeholder & Communication Plan
Part A maps who matters and how much. Part B turns that map, plus the RACI, into an actual schedule of communications.
How to use — revisit the stakeholder map at each stage gate. Build the communication plan from it: who needs what, how often, and in what format.
Project | Customer Portal Launch | Reference | 2026-001 | Review date | 30 Jun 2026
Part A — Stakeholder Map
Stakeholder / group | Role | Interest (L/M/H) | Influence (L/M/H) | Quadrant | Engagement approach
Project Sponsor | Chairs SteerCo, final approver | High | High | Manage closely | Weekly Update; every SteerCo
Business Owner | Accountable for benefits realisation | High | High | Manage closely | Weekly Update; every SteerCo
SteerCo members | Governance forum | High | High | Manage closely | SteerCo Pack each cycle
Project team | Delivers the work | High | Medium | Manage closely | Daily/weekly team meeting
SSO vendor | Delivers SSO integration (RACI004) | Medium | Medium | Monitor -> Manage closely during integration (M4) | Ad hoc; weekly check-in added during integration
BoM | Portfolio governance | Low | High | Keep satisfied | Monthly Report to BoM (portfolio roll-up)
End users | Use the finished portal | High | Low | Keep informed | Milestone update; UAT invitation (M5)
Part B — Communication Plan
Communication / meeting | Purpose | Audience | Frequency | Format / method | Owner
Kick-off meeting | Align all stakeholders on scope, roles, and plan | All stakeholders | Once, before delivery starts | Meeting | Project Manager
Weekly Update | Short-cycle status to stakeholders | Project Sponsor, Business Owner, wider stakeholder list | Weekly | PowerPoint, emailed | Project Manager
Team meeting | Review task status and plan the coming week | Project team | Weekly | Meeting | Project Manager
SteerCo Pack & meeting | Governance decisions, risk and change review | SteerCo members | Each SteerCo cycle | Meeting + pack | Project Manager
Monthly Report to BoM | Portfolio-level roll-up of project status | BoM, PMO | Monthly | Excel report | PMO
SSO integration check-in | Track vendor delivery during a critical dependency | SSO vendor, PM, IT | Weekly, for the 4-week integration window (M4) | Call | Project Manager
Closure & lessons learned review | Confirm delivery, capture lessons for future projects | Project Sponsor, Business Owner, project team | At project closure | Meeting + Closure Report | Project Manager